## ورقة1
Risk | Probability | Impact | Planning Strategy | Action
Suppliers delay | High | High | Avoid | Getting supplies from local companies to save time
Servers Crashing | Low | High | Mitigate (Impact) | Making sure to have Database Backup
Development delay | Medium | High | Transfer | Use an Insurance incase SW delivery delay