## ورقة1
Project Budget = 10000 Hrs
Assume that Engineers working hours / day is 8 Hrs, 5 days / week , 25 days / month
Working time / month for 5 Engineers = 5 * 8 * 25 = 1000 Hr / month
Project duration per month : 10000 / 1000 = 10 months
Current project status = 7000 Hrs
Project status in month : 7000 / 1000 = 7 months = 175 days
Earned Value : 55% * 10000 = 5500 Hrs
Actual cost = 7000 Hrs
Is the project over-budget? Yes
Over-Budget = 7000 - 5500 = 1500 Hrs
Is the project delayed? Yes
Planned value = ( Project status in month / Project period in month ) * 10000
= ( 7 / 10 ) * 10000
= 7000 Hrs
Delay in project = 7000 - 5500 = 1500 Hrs
Delay in days = 1500 / (5*8) = 37.5 = 38 days
| Month | Planned | Actual | Earned
| 0 | 0 | 0 | 0
| 1 | 1000 | 1000 | 786
| 2 | 2000 | 2000 | 1571
| 3 | 3000 | 3000 | 2357
| 4 | 4000 | 4000 | 3143
| 5 | 5000 | 5000 | 3929
| 6 | 6000 | 6000 | 4714
| 7 | 7000 | 7000 | 5500
| 8 | 8000 | 8000 | 6285
| 9 | 9000 | 9000 | 7071
| 10 | 10000 | 10000 | 7857